## Sheet1
Sprint 1 Planning Sept. 29 - Oct. 10
Task | Estimate | Assigned to | Problems | Notes
Client Interview | 2 hours | Everyone | We were unsure of if would would have sufficient information
Help the Designers | 2 hours | Max and Ghebre
Staging Server | 1 hour | Ghebre | NA | gebgebonline.com/stagingarea
WordPress installation | 1 hour | Ghebre | NA | We used the amazon web service guide for our vps
Standup Meeting | 15 minutes | Everyone | NA
Initial Theme Creation | 1 hour | Max | NA
Github Sync Setup | 1 hour | Max and Ghebre | NA
Standup Meeting | 15 minutes | Everyone | NA
Build Tasks: Grunt/LESS | 2 hours | Max and Ghebre | Learning Curve | We will expect help from our instructor
Theme Hierarchy Stubs | 1 hour | Max and Ghebre | Learning Curve | We will expect help from our instructor
Sprint 1 Retrospective Sept. 29 - Oct. 10
Task | Estimate | Actual | Assigned to | Issue # | Notes
Client Interview | 2 hours | 2 hours | Everyone |  | Complete
Help the Designers | 2 hours | 2 hours | Max and Ghebre |  | Complete
Staging Server | 1 hour | 3 hours | Ghebre | NA | Complete
WordPress installation | 1 hour | 1 hour | Ghebre | NA | Complete
Standup Meeting | 15 minutes | 10 minutes | Everyone | NA | Complete
Initial Theme Creation | 1 hour | 1 hour | Max | NA | Complete
Github Sync Setup | 1 hour | 1 hour | Max and Ghebre | NA | Complete
Standup Meeting | 15 minutes | 10 minutes | Everyone | NA | Complete
Build Tasks: Grunt/LESS | 2 hours | 2 hours | Max and Ghebre | 3 | Complete
Theme Hierarchy Stubs | 1 hour | 1 hour | Max and Ghebre | 3 | Complete
Sprint 2 Planning Oct. 13 - Oct. 24
Task | Estimate | Assigned to | Problems | Notes
Basic theme layout vis-a-vis designer's wireframes | 4 hours | Everyone
Custom post types (1 task each) | 4 hours | Max and Ghebre |  | Post, Page, Attachment, Revision, Navigation, and menu
Plugin planning and installation | 1 hour | Max and Ghebre
Basic styling | 1 hour | Everyone
Menu setup and information architecture | 1 hour | Everyone
Standup Meeting | 15 minutes | Everyone